## Slide 1: ISIS PDR Preparations
Scott Weidner, SwRI

## Slide 2: PDR is Tomorrow
2

## Slide 3: Logistics
3
PDR will be on November 5th and 6th
  At SwRI
  In Bldg 263 Presentation Room
Two Completely Full Days
  EPI-Hi
  EPI-Lo
  SOC
Social Event evening of the 5th

## Slide 4: Goals of PDR
4
Overall
  Requirements known
  Plans made
  Preliminary designs complete
  Analyses performed
  TRL 6 demonstrated
We are well-positioned to exceed expectations

## Slide 5: Schedule to PDR
5
08/19 – receive presentation .ppt with outline for every presentation with presenter assignment
        Turn into a rough draft
          Fix outline, get the easy slides done, main idea for each slide
09/02 – rough draft review
        Turn into a decent draft:
          Placeholders for all art
          Attempt at all words
09/16 – decent draft review
        Turn into a good draft
          All Art in place
          Tell the full story
09/30 – good draft review
        Finalize presentations
          Correct all artwork issues
          Tweak words
10/14 – flip-thru final draft
        Authors make updates
10/21 – final presentation complete
        Publication preps
10/28 – send out final presentation
        Reviewers review the material

## Slide 6: Philosophy
6
Take Pictures Everyday
  Shoot First … Ask Questions Later
No walk-on charts … let’s get it right
If we write to this early schedule,
  we’ll know what’s missing
  can focus on the hard stuff