## Slide 1: Action Items
Nigel Angold
Notes: introduction

## Slide 2: Outline
Sources of Action Items
SwRI Action Item Tracking
APL / Caltech Action Item Tracking
ISIS Action Items from Meetings
Summary of ISIS Action Item Tracking

## Slide 3: Sources of Action Items
No action items assigned to ISIS at MDR
Other action items:
  from PDR, CDR, SIR, PER, PSR
  from Peer Reviews
  from I&T
  from Fabrication Readiness Reviews, Test Readiness Reviews etc.
  from SPP-ISIS meetings
  from internal ISIS meetings

## Slide 4: SwRI Action Item Tracking
SwRI has its own tracking system for action items:
Project Information Management System – Action Item Management PIMS-AIM
  PIMS-AIM tracks the action item history and automatically distributes status updates, due date reminders, closure memos.
  The ISIS Project Manager is responsible for PIMS-AIM.
  The ISIS Systems Engineer (SE) is responsible for tracking the disposition of ISIS action items.
  For reviews, in addition to PIMS-AIM tracking, an Internal Design Review Report (IDRR) form is generated and signed off by the review chair when all action items are closed.

## Slide 5: SwRI Action Item Tracking
  PIMS-AIM will be used to track action items from:
  PDR, CDR, SIR, PER, PSR
  EPI-Hi Peer Reviews
  EPI-Hi I&T
  EPI-Hi FRRs, TRRs
  At the end of a review, action items are re-visited, summarized and documented, written inputs from reviewers collected.
  Action item materials are posted on the ISIS Wiki.

## Slide 6: APL / Caltech Action Item Tracking
  APL has its own tracking systems which the EPI-Lo team will use for lower level action items e.g. for peer reviews:
  Post-review, a memo is circulated to all review participants and ISIS management which lists all action items.
  At APL, action items are recorded in an Excel spreadsheet and tracked by the EPI-Lo team. This is periodically distributed as work on each action item progresses.
  Action Item Response memos are circulated to all review participants and ISIS management summarizing the disposition of each action item until all have been closed.
APL will use SwRI’s PIMS-AIM for higher level action items e.g. from PDR, CDR etc. and is always available to EPI-Lo as a backup tracking mechanism.
Caltech will use the SwRI action item tracking tools.

## Slide 7: ISIS Action Items from Meetings
  For tracking actions items from SPP-ISIS meetings and internal ISIS meetings:
  Action items arising during meetings are noted in the minutes and an actionee and due date are assigned.
  Progress is tracked during subsequent meetings and noted in the minutes.
  Action items remain in the meeting minutes until they are closed.
  The SPP Payload Systems Engineer (SE) is responsible for tracking action items arising from SPP-ISIS meetings.
  The ISIS SE is responsible for tracking the disposition of ISIS action items from internal meetings.

## Slide 8: Summary of ISIS Action Item Tracking
Action Items from | SwRI | APL | Caltech
PDR, CDR etc. | PIMS-AIM | PIMS-AIM | PIMS-AIM
Peer reviews | PIMS-AIM | Memos, spreadsheet | PIMS-AIM
I&T | PIMS-AIM | Memos, spreadsheet | PIMS-AIM
FRR, TRR etc. | PIMS-AIM | Memos, spreadsheet | PIMS-AIM
Meetings | Minutes | Minutes | Minutes

## Slide 9: Summary of ISIS Action Item Tracking
  SwRI has the tools to track ISIS action items.
  Institutional tracking tools will be used by the EPI-Lo team at APL to track lower level action items (PIMS-AIM is available as a backup tracking system).
  High level EPI-Lo action items will be tracked with SwRI’s tracking tools.
  SwRI’s tools will be used to track all EPI-Hi action items.
  Action items arising from meetings are being tracked through meeting minutes.
  All ISIS action items are being effectively tracked.