## Slide 1: Action Items
Nigel Angold
Notes: introduction

## Slide 2: ISIS Action Items
No actions assigned at the MDR
None self-imposed by the team
Actions from Peer Reviews EPI-Lo:
  EPI-Lo TOF and CFD ASIC peer review ???
  EPI-Lo Sensor Peer Review 5/22/13
  EPI-Lo Anode Board Peer Review 6/21/13
  EPI-Lo Sensor Peer Review 8/19/13 - 8/20/13
  EPI-Lo Event Board Peer Review 8/21/13
  EPI-Lo LVPS Peer Review 8/21/13
  EPI-Lo HVPS Peer Review 8/21/13
  EPI-Lo Energy Board Peer Review 8/26/13
  EPI-Lo Software Inheritance/Peer Review 9/11/13

## Slide 3: ISIS Action Items
No actions assigned at the MDR
None self-imposed by the team
Actions from Peer Reviews EPI-Hi:
  EPI-Hi PHASIC and Housekeeping ASIC Peer Review 12/6/12
  EPI-Hi LVPS Board Peer Review 5/22/13
  EPI-Hi DPU Board Peer Review 9/9/13
  EPI-Hi HET/LET Telescope Boards Peer Review 9/9/13
  EPI-Hi SSD Bias Supply Peer Review 9/23/13
  EPI-Hi Mechanical Peer Review 9/30/13
  EPI-Hi Software Inheritance/Peer Review 10/11/13

## Slide 4: ISIS Action Items
EPI-Lo TOF and CFD ASIC peer review ???
Actionee | Action Item | Status

## Slide 5: ISIS Action Items
EPI-Lo Sensor Peer Review 5/22/13
Actionee | Action Item | Status
Nelson | Make ground "targets" surrounding HV on a LV side of the PWB to protect LV circuitry from discharges. | Closed
Layman | Remove Ultem cover and associated spring washer on 3kV lug connection. | Closed
Layman | Make 900V guard washer out of plastic and eliminate Kapton spacer. | Closed
Layman | Vent all fasteners: 1) Vented Screws. 2) Vent trapped volume sideways by drilling in below threads. | Closed
Layman | Use aluminum tape to close the gaps between the wedges for UV purposes. | Open
Layman | Consider using bevel washer on screw for the 1000V to the side wall to avoid loss of contact due to material creep. | Closed

## Slide 6: ISIS Action Items
EPI-Lo Sensor Peer Review 5/22/13
Actionee | Action Item | Status
Nelson | Increase distance around the 3000V components on the anode board component side. Is the decoupling 3000V cap needed? | Closed
Nelson | If HV standoff is run at room temperature rather than our expected max temp in test/qual, we may need to increase the HV to compensate (e.g. 3600V  4000V). | Open
Layman | Reshape the 1kV and 2-9kV lug to provide more separation from the side wall, and open hole. | Closed
Nelson | Use blocking cap and CSA to look for discharges. | Closed
Weidner | Give identifier of Kapton sheet used in PWB stackup for IES | Closed
Layman | Shape the insulator between the cover and the 1kV volume so that the surface path along the insulator surface is at least 3mm. For example, "T" shaped or "U" shaped. | Closed

## Slide 7: ISIS Action Items
EPI-Lo Anode Board Peer Review 6/21/13
Actionee | Action Item | Status
Nelson | Verify that embedded capacitor will not fail. Consider looking at standard HV cap testing/temp cycling, testing at higher voltages, possibly looking at x-rays for voids, etc. Need to execute well documented test plan early in program. | Open
Nelson | Consider using Kapton 8525 (dielectric strength of ~6kV/mil. ) or compare it with planned material. | Closed
Nelson | Time Constant of individual pads: can we make the resistor smaller to deal with higher rate situations? Need to look at capacitance to ensure it is ok. | Closed
Nelson | 3x is not a lot of derating for materials. Consider changing or justifying. | Closed
Nelson | Determine how to test ground plane arcing. Look at the size of discharge as if you completely dissipated full bypass caps. | Open
Nelson | Investigate the plasma-etch step for in-house Parylene. | Closed

## Slide 8: ISIS Action Items
EPI-Lo Sensor Peer Review 8/19/13 - 8/20/13
Actionee | Action Item | Status
Hill/Mitchell | Photo electron fluxes getting through pin holes created by dust. Could create a lot of false starts. Consider mitigations (e.g. -5V electric field). | Open
Nelson | Determine if the MCP count rate area density (counts/cm²) exceeds 1 MHz/cm². | Open
Hill | Generate a table of expected rates for bounding assumptions of radical drop-off and for characteristic rates of electrons, protons, He, and heavy ions. Document the foil efficiency foreground and background calculations, including assumptions on pinholes, efficiencies, dust environment, etc. Document the overall rate calculations and their assumptions. | Open
Hill | Improve the GEANT modeling to more realistically represent the sensor shielding configuration and re-assess the S/N. Investigate trades between S/N and cover mass. Consdier adding a witness detector to decrease the uncertainty in background. | Open

## Slide 9: ISIS Action Items
EPI-Lo Sensor Peer Review 8/19/13 - 8/20/13
Actionee | Action Item | Status
Nelson | Develop a strategy for keying or identifying the coax cables to avoid incorrect connections. | Open
Westlake | Launch electrons at all possible locations inside sensor model and characterize possible e- backgrounds. | Open
Nelson | Use redundant information to reject false signals. Consider using STI1 vs. STOP, ST2 vs. STOP, ST1 vs. ST2 redundant information to calculate "golden events" that are self consistent and are probably not corrupted by multiple starts from H+ or penetrators. | Open
Stokes | Provide peer reviewed reference for continuous test pulser technique for rate correction. | Open
Layman/Nelson | Consider HV discharge effects. | Open
Layman | Examine all fasteners without locking feature and consider high torque. Make sure no plastics in the stackup. | Open

## Slide 10: ISIS Action Items
EPI-Lo Sensor Peer Review 8/19/13 - 8/20/13
Actionee | Action Item | Status
Layman | Remove webbing, stabilize wishbone with tongue and grooves to cover, or screw through cover. | Open
Cooper | Consider collimator designs that do not require bonding. | Open
Hill | Address EPI-Lo/EPI-HI energy gap in the L3 requirements. | Open
 | With the use of thicker foils on some openings, determine if one lookup table is sufficient. If not, change the baseline to multiple tables or an alternate approach. | Closed
Mitchell | Consider putting double foils on the look directions that are close to the sun and near the ram direction for better pinhole tolerance. | Open
Hill | Consider the background rate from neutrals that are rammed into the opening, photo electrons from the sun shield, or low energy plasma. Are there any concerns? | Open
Hill | Investigate sending extra raw data down in telemetry to “fill in” unused telemetry allocation. | Open

## Slide 11: ISIS Action Items
EPI-Lo Sensor Peer Review 8/19/13 - 8/20/13
Actionee | Action Item | Status
Gurnee | Consider building up full spare MCP assemblies. How many would be needed, how would they be matched to appropriate quadrant pair and how much testing would they have? | Open
Layman | Vent the back cover of the SSD assembly. | Open
Layman | Add holes/mounting interfaces to the structure to support red tag cover and handling fixture | Open
Layman | Detetermine to mark/serialize the foils. | Open
Layman | Consider the best way to route purge through the sensor, taking into account the need for launch pressure profile venting. | Open

## Slide 12: ISIS Action Items
EPI-Lo Event Board Peer Review 8/21/13
Actionee | Action Item | Status
Gurnee | Put 18pF caps directly between (-) and (out) pins on op-amps with complicated drive circuits. - Use 0.1 low temp co 10.0K for R768 - Make R8̴9 ≈ R86 ıı R768 | Closed
Gurnee | Global resets driven by FPGA and not the specially designed reset chips with guaranteed low voltage performance. | Open
Gurnee | Use 0.1%, low temperature coefficient, divider resistors on all ref circuit precision resistors. | Closed
Gurnee | Examine "design to min and max current" with respect to total line impedance and resistance. - Consider using a voltage sense line to the LVPS. | Closed
Gurnee | Consider using: 0603 0.1 uF, tantalum (small, yellow SMT) 220uF, 10V. | Closed
Gurnee | Evaluate if CKT guarantees VA ≥ VD for A128. | Open

## Slide 13: ISIS Action Items
EPI-Lo LVPS Peer Review 8/21/13
Actionee | Action Item | Status
Do | Input CM range goes to gnd, but must be 50mV above negative rail. Consider powering op-amp from - voltage or re-design circuit. | Closed
Do | Add over-voltage protection Zener. Evaluate transistor choice and if we need CR10 on puck LVPS. | Closed
Do | Demonstrate single fault conditions on 3.3V and verify it is ok (thermal, part stress, etc.). 1) Transformer winding short 2) Loss of control loop - full duty cycle 3) Add voltage monitor before 3.3 linear regulator and software can request a power off on fault 4) Look at what SPP DPU does | Open

## Slide 14: ISIS Action Items
EPI-Lo HVPS Peer Review 8/21/13
Actionee | Action Item | Status
Dickinson | Coordinate selection of HV safe connector with bracket and spacecraft. | Open
Do | Review effect of Zener temp coefficient. - Review effect of feedback division resistors temp coefficient - Consider additional HV monitor that would allow long term temperature adjustments. - Check to detemrine how stable it must be. | Open

## Slide 15: ISIS Action Items
EPI-Lo Energy Board Peer Review 8/26/13
Actionee | Action Item | Status
Gurnee | Determine the need/want/history of conformal coating. | Open
Nelson | Add filter to pam board on bias supply output. Look at puck Anode board for filter values. | Open
Gurnee | Ensure ground place on rigid-flex is on outside of rigid-flex (side away from center hole). | Closed
Goldsten | Consider pull-down resistors on SEL0 and SEL1 inputs to energy chip to protect from possible ESD damage during handling. | Closed

## Slide 16: ISIS Action Items
EPI-Lo Software Inheritance/Peer Review 9/11/13
Actionee | Action Item | Status

## Slide 17: ISIS Action Items
EPI-Hi PHASIC and H/K ASIC Peer Review 12/6/12
Actionee | Action Item | Status

## Slide 18: ISIS Action Items
EPI-Hi LVPS Board Peer Review 5/22/13
Actionee | Action Item | Status
Dickinson | Determine whether the redundant primary side power signals from the spacecraft can be tied together on the LVPS. | Closed
Dickinson | Work with Project to determine how Op Heater power is received by instrument. | Open
Do | Look into using freewheeling diodes around the normal mode inductors to reduce conducted emissions in EMI. | Open
Do | Consider fuses or series diodes across D8/D9 diodes to reduce single point failures. | Open
Do | Consider thermal analysis and part packaging for Q20. | Open
Do | Consider fast-and-soft Schottky across the switching FET (Q20). | Open
Do | Consider ferrite bead/small inductor for differential mode noise rejection on low voltage outputs. | Open

## Slide 19: ISIS Action Items
EPI-Hi LVPS Board Peer Review 5/22/13
Actionee | Action Item | Status
Do | Perform a short-circuit analysis for safety purposes on low-voltage outputs. | Open
Do | Verify that the resistance/capacitance between primary to secondary is within SPP EMI Spec. | Open
Do | Fix note "GNDP is tied to GND at U1-18”. | Open
Do | Add a page/key that indicates how grounds are connected. | Open
Do | Linear Regulator (U4) is positive feedback; it should be negative. | Open
Do | Determine what happens to other voltages when a voltage rail is shorted. | Open
Do | Consider active current limiting on the output of the linear regulators to prevent going to cycle-by-cycle limiting on the switcher. | Open
Do | Refine the output loads and provide capability table to EPI-Hi for review. | Open

## Slide 20: ISIS Action Items
EPI-Hi LVPS Board Peer Review 5/22/13
Actionee | Action Item | Status
EPI-Hi | Review min/max voltage and determine where error budget is bookept | Open
Do | If operational heater is added to primary power bus, do not include heater power in primary current sense circuit. | Open
EPI-Hi | Supply a thermistor (made to GSFC spec). | Open
Dickinson | Ensure Do has a contact for the thermal analysis. | Closed
Do | Perform a follow-up layout review. | Open
Dickinson | Determine when EPI-Hi need the LVPS in the schedule. | Closed
Do | Indicate on schematic which portions should have primary vs. secondary side EMI shielding to leave room on parts placement for gold-plated footprint. | Open
Do | Investigate putting electrostatic isolation between the primary and secondary transformer windings. | Open
Do | Look at using a reset winding. | Open

## Slide 21: ISIS Action Items
EPI-Hi DPU Board Peer Review 9/9/13
Actionee | Action Item | Status
Caltech | Provide mask for review. | Open
Caltech | Describe detector screening and what they will do to avoid leakage. | Open
Caltech | Leave adequate time for coupon testing. | Open
Crain (Aerospace) | Provide details of Aerospace Actel Lifetime testing configuration. | Open
Dickinson | Does Actel require 33 Ohm series resistor on every I/O? Does the FPGA core regulation have to be at the FPGA? Is a Hyperlynx analysis required? Check with Rick Conde. | Open
Caltech | Demonstrate that there is a 0.1 uF ceramic next to every power supply pin on the FPGA. | Open
Caltech | Provide series resistor at all clock drivers; consider snubber termination at source. | Open
Dickinson | Double check the control signal termination scheme matches HIS/EPI-Lo. | Open

## Slide 22: ISIS Action Items
EPI-Hi DPU Board Peer Review 9/9/13
Actionee | Action Item | Status
Caltech | Provide information on MRAM memory mapping in MISC. | Open
Caltech | Terminate unused inputs to the drivers (U6,U5). | Open
Caltech | Move the brackets on sheet 3 on the right. | Open
Caltech | Add series resistors on LVDS inputs. | Open
Caltech | Justify brown-out conditions for HK POR function. | Open
Caltech | Explore the power-supply sequencing/monitoring problem with LVPS; avoid failure modes. | Open
Caltech | Clocks need to be stable XX amount of time prior to CPU operation. Perform an analysis - required at CDR. | Open
Caltech | Prepare FPGA, memory, code utilization numbers for PDR. | Open
Caltech | Check on the full range of the current monitor provided by the LVPS. | Open
Caltech | Consider high-side switching on the operational heaters. | Open

## Slide 23: ISIS Action Items
EPI-Hi HET/LET Telescope Boards Peer Review 9/9/13
Actionee | Action Item | Status
Caltech | Provide detector noise analysis and worst case threshold/noise ratios. Provide expected livetime vs. deadtime. | Open
Caltech | Evaluate the need to use LVDS on telescope-DPU data line. | Open
Caltech | Investigate potential case of a failure in one telescope causing failure in others. | Open
Crain (Aerospace) | Provide details of regulator with FPGAs that resulted in no failures over millions of hours of testing. | Open
Caltech | Change R61 resistor value from 20k ohm to 10k ohm. | Open
Caltech | Are we implementing autonomous of balancing of the leakage current? If so, provide a description. | Open
Caltech | Consider connecting HV bias bypass capacitor to pre-amp 5V rather than to ground. | Open

## Slide 24: ISIS Action Items
EPI-Hi HET/LET Telescope Boards Peer Review 9/9/13
Actionee | Action Item | Status
Caltech | Provide table 3 in PHASIC handbook. | Open
Caltech | After low noise setup is complete, is the 0.2% crosstalk spec met and under what input and threshold conditions? | Open

## Slide 25: ISIS Action Items
EPI-Hi SSD Bias Supply Peer Review 9/23/13
Actionee | Action Item | Status

## Slide 26: ISIS Action Items
EPI-Hi Mechanical Peer Review 9/30/13
Actionee | Action Item | Status

## Slide 27: ISIS Action Items
EPI-Hi Software Inheritance/Peer Review 10/11/13
Actionee | Action Item | Status