## Slide 1: EPI-Hi Electronics
Branislav Kecman / Rick Cook
Notes: introduction

## Slide 2: EPI-Hi Electronics
Implementation and Status
Branislav Kecman
Cognizant Electrical Engineer

## Slide 3: Outline
Design/Assembly/Test Flow
Board Status
  DPU Board Layout
  Bias Supply Board Layout
EEE Parts Program and Status
  Significant Parts
  ASICs: PHASIC and HKchip
Resources
  Power
  Mass
Harness Diagram
  Thermal Harness

## Slide 4: Design/Assembly/Test Flow
Detailed design
and schematic
J. Burnham
B. Kecman
EM layout
J. Burnham
B. Kecman
Parts identification, EM and flight
B. Kecman, J. Burnham
J. Tumlinson SwRI
Parts stress
analysis
J. Burnham
EM assembly
J. Burnham
B. Kecman
Parts procurement, EM and flight
B. Kecman, M. Windhausen GSFC
Test/rework/test
R. Cook
B. Kecman
J. Burnham
Flight board
assembly & inspection
JPL
EM layout
review
SwRI
Flight board test
R. Cook
B. Kecman
J. Burnham
Staking,
conformal
coating
JPL
Mechanical design
S. Shuman
GSFC
Peer review
SwRI, JPL
Preliminary design
and schematic
R. Cook
J. Burnham
Flight layout
review
SwRI
Flight layout mods
J. Burnham
B. Kecman

## Slide 5: Board Status
Board | Spec | Schem | Peer review | EM layout | EM fab began | EM parts procured | EM test starts at Caltech
Telescope x3 | N/A | 80% | √ | 20% | No | 60% | Jan-Jun ‘14
DPU | N/A | √ | √ | √ | No | 80% | 2/28/14
LVPS | √ | √ | √ | √ | Yes | √ | 1/27/14
Bias Supply | √ | √ | √ | 60% | No | 70% | 4/7/14
Breadboard | Spec | Schem | Peer | Layout | Fab | Parts | Test
Bias Supply | √ | √ | N/A | √ | √ | 90% | In progress

## Slide 6: DPU Board Layout
13.50 cm, square
View from sunward direction

## Slide 7: Bias Supply Board Layout
View from sunward direction
17.50 cm
14 cm
13.50 cm

## Slide 8: EEE Parts Program and Status
All parts required to meet EEE-INST-002, Level 2
  PCB approval required for all parts
    PCB review in process for all parts
Existing Caltech custom databases used to track inventory and kit history for all parts
Procurement in process now for prototype/EM parts
Where possible, flight parts will come from Caltech, GSFC, SwRI and JPL inventory
  Parts more than 5 years old will have additional testing performed as required by the PCB

## Slide 9: Significant Parts
Part Number Part Type | Manufac-turer | Heritage | Notes
RTAX250SL-CQ208B FPGA | Microsemi SoC (Actel) | NuSTAR | Existing stock at Caltech
5962R0323601QXC SRAM, 4Mb (128k x 32) | Aeroflex | NuSTAR | Existing stock at Caltech
5962R0422701QXC SRAM, 16Mb (512k x 32) | Aeroflex |  | 
5962R1222201VXC MRAM, 16Mb (2M x 8) | Aeroflex |  | Common buy with S/C
10229545 PHASIC, Hybrid ASIC | JPL | STEREO | Existing stock at Caltech Modification required
TBD HKchip, ASIC | JPL |  | Will follow similar process as PHASIC

## Slide 10: ASICs: PHASIC and HKchip
PHASIC: Hybrid ASIC developed for STEREO
  Using existing stock with modifications
    New rad-hard wafers will be produced
      TID and SEL testing planned
    Heritage die will be removed and replaced
    Packaging will be performed by JPL Hybrid Lab
    Assembled part will undergo full screening and qualification performed by JPL and Caltech
HKchip: New part, monolithic ASIC
  Will follow the same wafer procurement, packaging and
  test plan as the PHASIC

## Slide 11: Resources - Power
End Of Life | 
Bias Supply @ End Of Life | 0.68
LVPS @ EOL (70% efficiency) | 1.74
Total @ EOL | 5.8
Subsystem | Power [ W ]
LET1 board | 1.06
LET2 board | 0.76
HET board | 0.95
DPU board | 0.62
Bias Supply @ Beginning Of Life | 0.12
LVPS @ BOL (70% efficiency) | 1.50
Total @ BOL | 5.0

## Slide 12: Resources - Mass
Subsystem | Mass [ g ]
LET1 telescope LET1 board | 225 258
LET2 telescope LET2 board | 145 233
HET telescope HET board | 120 250
DPU board Bias Supply & RF shields LVPS & RF shields | 197 225 + 130 160 + 100
Elec. box, hardware & shielding Telescope brackets Thermal hardware MLI blankets | 925 + 250 +100 160 50 100
Total | 3,628

## Slide 13: Harness Diagram

## Slide 14: Thermal Harness Diagram