## Slide 1: Risk Status
John Dickinson
ISIS SE (SwRI)

## Slide 2: Outline
Risk Analysis Score Card
Likelihood/Consequence implementation for ISIS
Risk Summary
Top Risks
Risk Description
  Autonomy Concerns
  Technical Risks
  Risks with Likelihood and Consequence < 2
  Mitigated Concerns
  New Risks

## Slide 3: Risk Analysis Score Card
Likelihood Bins | Safety (likelihood of safety event occurrences) | Technical (Estimated likelihood of not meeting mission technical performance requirements) | Cost/schedule (Estimated likelihood of not meeting allocated Cost/Schedule requirements or margin)
5 Very High | (Ps > 10-1) | (PT > 50%) | (PCS > 75%)
4 High | (10-2 < Ps ≤ 10-1) | (25% < PT ≤ 50%) | (50% < PCS ≤ 75%)
3 Moderate | (10-3 < Ps ≤ 10-2) | (15% < PT ≤ 25%) | (25% < PCS ≤ 50%)
2 Low | (10-6 < Ps ≤ 10-3) | (2% < PT ≤ 15%) | (10% < PCS ≤ 25%)
1 Very Low | (Ps ≤ 10-6) | (0.1% < PT ≤ 2%) | (PCS ≤ 10%)
LEVEL | Minimal (1) | Minor (2) | Medium (3) | Major (4) | Very High (5)
Safety | Negligible safety impact | Minor injury with no lost work time | Injury with lost work time | Severe injury | Death or permanent disabling injury
Technical | Negligible technical impact | Decrease in instrument capability/margin. But all instrument requirements met, or need for requirement definition or design/implementation workaround | Major loss of instrument capability | Loss of Instrument (EPI-Hi or EPI-Lo) | Loss of one or more Level-1 science requirements
Cost | ISIS Project cost overrun of less than 1% of allocated | ISIS Project cost overrun between 1% to 3% of allocated | ISIS Project cost overrun between 3% to 10% of allocated | ISIS Project cost overrun between 10% to 20% of allocated | ISIS Project cost overrun of greater than 20% of allocated
Schedule | Negligible schedule slip | Schedule slip not on critical path | Schedule slip affecting critical path but not launch or post-launch critical event | Schedule slip of 1 to 3 months | Schedule slip of greater than 3 months

## Slide 4: Likelihood/Consequence for SPP Plans/Risks
SPP Plans:
  Likelihood: The likelihood the project will implement the plan x the likelihood the plan will affect ISIS
  Consequence: If the plan were to be realized, how much would it impact ISIS.
Risks:
  Likelihood: The likelihood the risk will affect ISIS
  Consequence: If the risk were to be realized, how much would it impact ISIS.
A note on Plans Mitigation Strategy
  Every SPP Plan can be accomplished by adding resources (mass/power, cost, schedule). These are quantified in the threats/liens spreadsheet, not as mitigations in the risks.
Notes: Spacecraft has requested that we track all technical challenges in this manner
Also has requested that all technology development items be entered as risks

## Slide 5
11 |  |  |  | 
 |  | 13 15 16 17 19 |  | 
 | 7 14 | 6 |  | 
 | 1 2 5 8 9 | 3 4 |  | 
18 12 |  | 10 |  | 
Risk Summary
1 2 3 4 5 Consequence
Likelihood 1 2 3 4 5

## Slide 6
 |  | 13 15 16 17 19 |  | 
 | 14 | 6 |  | 
 | 1 | 3 4 |  | 
Progression of Top Risks
1 2 3 4 5 Consequence
Likelihood 1 2 3 4 5
Rank | Trend | Risk ID | Approach | Risk Title
1 |  | 13 | R | SPP PLANS: ISIS Time Tagged Commands
2 |  | 15 | R | SPP PLANS: ISIS Increased Ground Software Demands Due to Autonomy
3 |  | 16 | R | SPP PLANS: ISIS Increased Instrument FSW Demands Due to Autonomy
4 |  | 17 | R | SPP PLANS: Configuring ISIS Based on Solar Distance
5 |  | 19 | R | SPP PLANS: ISIS Increased Autonomy
6 |  | 6 | R | RISK: ISIS Vibration Levels
8 |  | 3 | R | RISK: EPI-Hi LET Thin Windows and Dust Impact Susceptibility
9 |  | 4 | R | RISK: EPI-Lo Dust Impact Susceptibility
10 |  | 1 | R | RISK: EPI-Hi Thin Detector Availability
7 |  | 14 | R | RISK: ISIS Shock Testing
Med
High
Low
Criticality
L x C Trend
Decreasing (Improving)
Increasing (Worsening)
Unchanged
New Since Last Period
Approach
M - Mitigate
W - Watch
A - Accept
R - Research

## Slide 7: Autonomy Risks (Top 5 ISIS Risks)
As a result of the lack of heritage in the ISIS predecessor instruments implement instrument level heritage, ISIS has elevated several specific areas in which more work will be required:
  Implementation of Time Tagged Commands
  Ground software autonomy handling demands
  Flight software autonomy handling demands
  The ability to configure the instrument based on solar distance
  General concern about loss of science data due to autonomous operations
All of these issues will be high priority for clarification during phase C
Planned mitigations include:
  Analyzing scenarios and brain-storming operation conditions
  Working with autonomy experts to explore all conditions
  Updating the design concept to accommodate instrument autonomy implementation
  Peer reviewing our updates with autonomy experts
  Test potential autonomy conditions thoroughly
This accounts for our top 5 risks as a Project
  All items are Likelihood: 4, Consequence: 3
This is a testament to the experience of the instrument teams, the firm grasp on technical challenges to the instruments, and the firm grounding in heritage instruments

## Slide 8: Risk: ISIS Vibration Levels
Description ID: 6 | Given that SPP random vibration is a challenging requirement; there is a chance that instruments will not be capable of meeting the requirements,
Consequence | which will result in a late re-design of the instruments.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 3 | 
Status Message | Waiting on Project for more conclusive Coupled Loads Analysis results; also looking for sine vibe environment to be better defined by Project.
Mitigation Plan 1 Status: Expired Trigger Date: 02 Apr 2012 | Title: Deliver FEM Model to Project Description: Develop and deliver an FEM model to Project to enable Project analysis of vibration levels and iterate vibration requirements.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 May 2013 | Title: Mechanical Design, Analysis, and Testing Description: Prioritize mechanical design and analysis critical to ensuring the sensors survive vibration testing. Early Phase B vibration testing with the bracket and instrument mass models will validate the designs early enough to make changes if necessary.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 May 2014 | Title: Increase Structure Description: Increase structure of instruments to meet vibration levels.
Update mitigations/dates

## Slide 9: RISK: EPI-Hi LET Thin Windows and Dust Impact Susceptibility
Description ID: 3 | Given that thin windows are fragile and the mission dust environment could be harsher than initially expected; there is a risk that dust impacts could result in damage to the windows during flight,
Consequence | which will result in a compromise in the resolution of the EPI-Hi telescopes.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 2 | 
Status Message | EPI-Hi windows survived Heidelberg dust testing and showed stacked window configuration is effective at mitigating dust penetration to detectors. Even holes produced by penetrating particles result in very limited access of UV light to detectors.
Mitigation Plan 1 Status: Completed Trigger Date: 01 May 2013 | Title: Perform Dust Testing Description: The integrity of the windows in a stacked configuration will be tested in a dust environment to determine the efficacy of the windows in protecting the detectors from dust and maintaining structural integrity to block UV light.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Baffling for Dust Protection Description: If risk of catastrophic damage due to dust impacts does not appear acceptably low, EPI-Hi could increase the baffle size to limit the affected angle of dust on the detectors. Trade: mass is used to buy down damage risk.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Significant Thickness Increase Description: If risk of catastrophic damage due to dust impacts does not appear acceptably low, EPI-Hi could use significantly thicker window for LET2 (single ended) telescope. Trade: measurement quality is reduced to buy down catastrophic damage risk.

## Slide 10: RISK: EPI-Lo Dust Impact Susceptibility
Description ID: 4 | Given that foils, SSDs, and MCPs are fragile and the mission dust environment could be harsher than initially expected; there is a risk that dust impacts could result in damage to the foils, SSDs, or MCPs during flight,
Consequence | which will result in a compromise of the FOV of the EPI-Lo instrument.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 2 | 
Status Message | EPI-Lo collimators limit FOV of dust particles to the foils. A second foil has been added to reduce likelihood of penetrating particles. UTEP environmental model completed with angular dependence and extension to smaller dust sizes. Foils received, foil sample holders being fabricated for dust tests at dust beam in Colorado, expected in November. More analysis on background due to dust-produced holes in foils (e.g., light, solar wind electrons).
Mitigation Plan 1 Status: In Process Trigger Date: 01 Apr 2012 | Title: Improved Analysis Description: Analysis will determine the expected rate of impact and damage, and if necessary, an outer shield can be added and additional design effort will ensure the instrument is fault tolerant to impacts on an individual wedge.
Mitigation Plan 2 Status: In Process Trigger Date: 01 Nov 2013 | Title: Double Foils Description: Double foils with half the original thickness each could be used behind the collimators to act as a whipple shield to avoid detector damage due to dust. Trade: complexity in foil design is increased to buy down susceptibility to dust damage.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Increase Structure Description: Possible mass and/or power increase to design the instrument to be more fault tolerant.

## Slide 11: Risk: ISIS Shock Testing
Description ID: 14 | Given that the project plans to shock test the SPP instruments and no shock testing has ever been performed on any of the ISIS heritage instruments, there is a chance that additional structural support will be required by ISIS to endure the [rigorous] qualification test environment without damage;
Consequence | which will result in an increase in mass requirement.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 3 | 
Status Message | This level, though reduced, is still very high if it is meant to be applied at the instrument base. ISIS requests levels at the instrument mounting deck. Shock level in excess of 1000 g's at (in this case, at high frequencies) the instrument location are of concern.
Mitigation Plan 1 Status: In Progress Trigger Date: 27 May 2013 | Title: Define Shock Environment Description: Work with project to determine the actual shock environment and work towards determining acceptable levels to which the shock test may be performed without significant design change. Trade: analysis is used to buy down the consequence of the risk.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2013 | Title: Increase Structure Description: Increase the structure of the ISIS instrument to withstand the testing without concern for failure. Trade: mass is used to buy down the consequence of the risk.

## Slide 12: RISK: EPI-Hi Thin Detector Availability
Description ID: 1 | Given that improved detectors have to date not been produced reliably with adequate yield; there is a risk that the energy threshold of the detectors will be increased,
Consequence | which will result in a compromise in the resolution of the EPI-Hi telescopes.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | Two manufacturers have successfully fabricated L0 and L1 detectors. Test records to date have revealed no concerns with either manufacturer. Accelerator and lab tests have shown the L1 detectors from both Micron and LBNL and L0 detectors from Micron perform as required for measurements of energetic heavy ions. These tests did not yet include any L0 detectors from LBNL. L0 detectors from LBNL are awaiting back-side ion implantation at LBNL. A thin detector (L0) in thermal-vacuum life test at GSFC has had stable leakage current over more than a week at 40C. Total doses tests of L1 detectors from both manufacturers have been carried out at JPL up to 1.1 Mrad with no observable degradation of detector performance. Additions radiation doses on these detectors are planned.
Mitigation Plan 1 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Increase Detector Thickness Description: If thinnest detectors (10 micro-meter) were found to be too fragile to give an acceptable yield, would increase the thickness as appropriate and accept an increase in energy threshold.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Use STEREO Detectors Description: If neither development were to yield flight-quality detectors, would fall back to thicker detectors of conventional design (as on STEREO).
Notes: We’ve got 2 manufacturers that can make this – this is lowered considerably

## Slide 13: RISK: EPI-Lo Stray Light Impact Susceptibility
Description ID: 7 | Given that stray light exists in the SPP environment as both background coronal light and reflected glint from the spacecraft itself; there is a risk that stray light could enter through the optics and impact the detectors,
Consequence | which will result in a biasing of the desired measurements from the instrument.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 3 | 
Status Message | Updated FOV obstruction analysis conducted. More analysis on light attenuation in foils and impact on false start signal and on background solid state detector counts.
Mitigation Plan 1 Status: In Process Trigger Date: 01 May 2013 | Title: Environmental Stray-Light Analysis Description: Model background light environment, specifically light reflecting off of electrons and dust, across all wavelengths of light and accounting for variations in the direct spectrum of the sun as a blackbody.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Ray-Tracing Analysis Description: Model light reflected off of spacecraft and scattered back to instruments, specifically to instrument apertures, using ray tracing techniques.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Optics Baffling Description: Increase size of collimators and/or foil thickness above sensitive aperture areas on instrument to limit entrance of light and light impacting detectors. Possibly block off affected apertures.

## Slide 14: RISK: EPI-Lo Wedge Technology Development
Description ID: 10 | Given that the as proposed EPI-Lo wedge design based on two sensor wedges per anode board has a long start delay line; there is a risk that the mass resolution performance may result in poor 3He/4He separation because of reduced timing performance.
Consequence | which will result in the EPI-Lo design failing to meet the instrument species separation requirements at high energies (>1MeV) for high ratios (100:1 or 1000:1).
Overall Status: Accepted(Retired) Consequence: 3 Likelihood: 1 | 
Status Message | TRL6 demonstration on quadrant wedge architecture has reduced risk likelihood. New CFDs are showing better performance. End-to-end testing on a full wedge has not yet occurred. We fully expect the new CFDs to perform better with the wedge. Upon successful testing, risk may be retired.
Mitigation Plan 1 Status: In Progress Trigger Date: 20 Sep 2012 | Title: Quadrant Design Description: The baseline plan is to use the 4 anode boards with 3 preamplifiers per board. Advantage is that this would require less resources (power/mass), but TOF measurement has not been adequately demonstrated.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Sep 2013 | Title: Accept lower mass resolution Description: If the Quadrant design does not perform as expected, we can use the lower mass resolution, as long as the loss of performance does not affect the L1 requirements.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2013 | Title: Octant Design Description: A backup plan is to use 8 separate anode boards with 3 preamplifiers per board. This option provides the cleanest measurement and separation of the ions, but adds power and mass.
Notes: Done - close

## Slide 15: Risks with Likelihood/Consequence < 2
Given that design and fabrication of a new Rad-Hard PHASIC could prove prohibitively challenging, there is a risk that existing STEREO chips would need to be used; which will result in an increase in mass for spot shielding.
  Good linearity and low thermal noise of new Rad-Hard PHASIC prototypes means that the targeted improvement in dynamic range has been met.
Given that design and fabrication of an EPI-Lo TOF ASIC could prove prohibitively challenging; there is a risk that EPI-Lo will be required to use existing TOFAs, which will result in an increase in mass and power resources required and a decrease in performance.
  EPI-Lo has selected test house for final qualification and working with test house to develop tests and test procedures.
Given that EPI-Lo has a max operating temperature of 30C and the Project expects EPI-Lo to operate at this temperature at Perihelion (prime science); there is a risk that operating at the max op temp will result in reduced resolution of the solid state detectors, which will result in a reduction in performance of the detector
  EPI-Lo has received SSDs from Canberra, mounted them into Ultem carrier, and completed fabrication and assembly of the energy board. Testing has begun.
Given that the spacecraft is planning to cant the spacecraft at 1AU in order to warm the radiators behind the heat shield; there is a risk that EPI-Hi windows will be facing the sun, which could result in thin windows covering LET telescopes to overheat and fail, possibly causing damage to the EPI-Hi detectors.
  Goddard solar simulator will work for EPI-Hi solar illumination test. In Process: Determine correct thermal coating for aluminized polyimide windows and run thermal analysis.

## Slide 16: SPP Plans that have been mitigated
Given that the SPP Project is considering updating EMI requirements for Deep Dielectric Discharge, there is a chance that the Project will require all instrument box walls to be 54 mils thick; which would result in a significant mass increase to the ISIS instrument.
  Deep Dielectric Discharge requirements were released that did not require box wall thickness increases
Given that the SPP Project is considering updating EMI requirements to exclude switching circuits in power supplies, there is a chance that portions of the ISIS LVPS will have to be redesigned; which would result in a significant power increase due to loss of efficiency in non-switching supplies and a schedule delay in the delivery of the EM LVPS to EPI-Hi and EPI-Lo.
  LVPS design moved away from the use of POL
Given that the project is requiring worst case circuit analysis to be performed on all circuits in the design, there is a chance that the ISIS team will be required to perform more analysis than was originally budgeted; which will result in increased cost and schedule delays.
  Worst case analysis required on safety critical circuits only

## Slide 17: Recent Risks (1 of 2)
Given that the SPP spacecraft is dynamic and movement of spacecraft components can affect instrument parameters, such as FOV; there is a chance the spacecraft could move or change something on the spacecraft into the ISIS FOV, which would result in reduction in quality of science data and could compromise satisfaction of mission science requirements.
  Consequence: 3 (technical), Likelihood: 2 (2% - 15%)
  Mitigation #1: Carefully track configuration control with the spacecraft
  Mitigation #2: Ensure all changes to position of spacecraft components are vetted with instrument teams
Given that the SPP Spacecraft can not send commands to the instrument; there is a chance that the spacecraft will remove power from the instrument in the case of certain fault conditions, which will result in the loss of forensic data in volatile memory required to diagnose the problem.
  Consequence: 3 (technical), Likelihood: 2 (2% - 15%)
  Mitigation #1: Explore fault conditions
  Mitigation #2: Enable low level commands to reboot instruments
Given that EPI-Hi is very sensitive to noise in it’s measurements and the power supply has switching low voltage conversion; there is a chance that noise from the power supply could increase the instrument noise floor, which will result in the reduction in quality of science data.
  Consequence: 2 (technical), Likelihood: 2 (2% - 15%)
  Mitigation #1: Emphasize noise reduction in power supply design
  Mitigation #2: Plan rigorous testing between instrument and power supply

## Slide 18: Recent Risks (2 of 2)
Given that the demand for the calibration facility that EPI-Hi was planning to use has been updated and grown in popularity, there is a chance that scheduling the facility will be challenging, which will result in a slip in the date for full calibration or an increase in cost to go to a different facility.
  Consequence: 1 (cost, schedule), Likelihood: 3 (15% - 25%)
  Mitigation: Schedule facility well in advance
Given that the cost for the calibration facility that EPI-Lo was planning to use has increased, there is a chance that scheduling the facility will be challenging, which will result in a slip in the date for full calibration or an increase in cost to go to a different facility.
  Consequence: 1 (cost, schedule), Likelihood: 3 (15% - 25%)
  Mitigation: Schedule facility well in advance
Given that [SOMETHING], there is a chance that EPI-Lo will require two sets of carbon foils where one was budgeted, which will result in an increase in instrument cost.
  Consequence: 1 (cost, schedule), Likelihood: 3 (15% - 25%)
  Mitigation:
Given that the allocated time for on-orbit instrument calibration is less than what was initially requested, there is a chance that EPI-Lo will have inadequate calibration time to collect statistics prior to the first encounter phase, which will result in a reduction in the usefulness of the first encounter data.
  Consequence: 2 (technical), Likelihood: 2 (2% - 15%)
  Mitigation: Work with Project to utilize other available time for calibration (week before combined calibration)

## Slide 19: Summary
ISIS risk process is effective and active
ISIS has made tremendous progress in driving down and mitigating risks
The ISIS instruments are technically sound, well understood, and corroboration with the spacecraft team is effective

## Slide 20: Backup

## Slide 21: SPP PLANS: ISIS Time Tagged Commands
Description ID: 13 | Given that the SPP Project is considering devolving the implementation of Time Tagged Commands to the Instruments, there is a chance that implementing a feature that has historically been performed by the spacecraft would require extra technical, financial, and schedule resources and might also incur extra IV&V scrutiny on the part of all instruments on the SPP spacecraft;
Consequence | which would result in duplication of effort, inconsistency of design, incompleteness of coordinating testing, and excessive expenditures of precious resources.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 4 | 
Status Message | ISIS is working with the Project to better understand the impact instrument autonomy as implemented on SPP will have. ISIS must implement a command handler to enable execution of commands at specific. This function was implemented in the spacecraft on ISIS heritage instruments.
Mitigation Plan 1 Status: In Progress Trigger Date: 30 Jan 2013 | Title: Analyze and Quantify Impact Description: Work with Project to see if this normally available service can still be provided to the Instruments
Mitigation Plan 2 Status: In Progress Trigger Date: 01 July 2013 | Title: Implement Design Change Description: Design new software and add extra coding and testing time.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Jan 2014 | Title: Test Description: Reduce risk of lack of well-coordinated and tested time-tagged commands by adding additional spacecraft and instrument ground testing resources.

## Slide 22: SPP PLANS: ISIS Increased Ground Software Demands Due to Autonomy
Description ID: 15 | Given that the project is planning to operate the spacecraft autonomously during most mission phases with minimal S/C FSW oversight of the instruments, there is a chance that the instrument ground software will be required to perform more rigorous vetting and error checking and experience more oversight than was original planned;
Consequence | which will result in an increase in ground software cost, complexity, and/or schedule slip.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 4 | 
Status Message | ISIS is working with the Project to better understand the impact instrument autonomy as implemented on SPP will have. ISIS must implement various error checking that is above our experience on heritage instruments. This will affect both ground and flight software.
Mitigation Plan 1 Status: In Progress Trigger Date: 30 Jan 2013 | Title: Project Assistance Description: Work closely with the project to understand and implement autonomy and help deter increased oversight. Aid from project will help instrument teams anticipate challenges with which they have not had to deal in the past.
Mitigation Plan 2 Status: In Progress Trigger Date: 01 July 2013 | Title: Work with Autonomy Experts for Assistance Description: Hire expert consultants who have experience with spacecraft autonomous operations in order to aid design instrument autonomous operations to handle unforeseen conditions.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Jan 2014 | Title: Autonomy Peer Reviews Description: Hold peer reviews on the instruments planned autonomy measures to vet instrument autonomous operations.

## Slide 23: SPP PLANS: ISIS Increased Instrument FSW Demands Due to Autonomy
Description ID: 16 | Given that the project is planning to operate the spacecraft autonomously during most mission phases with minimal S/C FSW oversight of the instruments, there is a chance that the instrument FSW will be required to perform more rigorous vetting and error checking and experience more oversight than was original planned;
Consequence | which will result in an increase in ground software cost, complexity, and/or schedule slip.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 4 | 
Status Message | ISIS is working with the Project to better understand the impact instrument autonomy as implemented on SPP will have. ISIS must implement various error checking that is above our experience on heritage instruments. This will affect both ground and flight software.
Mitigation Plan 1 Status: In Progress Trigger Date: 30 Jan 2013 | Title: Project Assistance Description: Work closely with the project to understand and implement autonomy and help deter increased oversight. Aid from project will help instrument teams anticipate challenges with which they have not had to deal in the past.
Mitigation Plan 2 Status: In Progress Trigger Date: 01 Nov 2013 | Title: Work with Autonomy Experts for Assistance Description: Hire expert consultants who have experience with spacecraft autonomous operations in order to aid design instrument autonomous operations to handle unforeseen conditions.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Jan 2014 | Title: Autonomy Peer Reviews Description: Hold peer reviews on the instruments planned autonomy measures to vet instrument autonomous operations.

## Slide 24: SPP PLANS: Configuring ISIS Based on Solar Distance
Description ID: 17 | Given that the project is planning to operate the spacecraft autonomously during most mission phases with uncoordinated instrument commanding and the instruments need to be able to configure themselves at power-up and to change their operational mode without spacecraft commanding, there is a chance that the instruments will have to increase their flight software capabilities or rely on a promising, but low-heritage concept of self-configuration based on solar distance;
Consequence | which could result in increased flight software complexity, increased cost, and delayed the schedule.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 4 | 
Status Message | ISIS is working with the Project to better understand the impact instrument autonomy as implemented on SPP will have.
Mitigation Plan 1 Status: In Progress Trigger Date: 27 May 2013 | Title: Project Assistance Description: Work closely with the project to understand and implement autonomy and help deter increased oversight. Aid from project will help instrument teams anticipate challenges with which they have not had to deal in the past.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Work with Autonomy Experts for Assistance Description: Hire expert consultants who have experience with spacecraft autonomous operations in order to aid design instrument autonomous operations to handle unforeseen conditions.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Jan 2014 | Title: Autonomy Peer Reviews Description: Hold peer reviews on the instruments planned autonomy measures to vet instrument autonomous operations and configuration based on solar distance.

## Slide 25: SPP PLANS: ISIS Increased Autonomy
Description ID: 19 | Given the relatively few real-time contacts, the need for autonomy, and the fact that instruments will be turned off repeatedly during data downlink activities, there is a chance that there will be an interruption in the operation of the instrument
Consequence | which results a loss of primary science data.
Overall Status: Accepted(Active) Consequence: 3 Likelihood: 4 | 
Status Message | ISIS is working with the Project to better understand the impact instrument autonomy as implemented on SPP will have.
Mitigation Plan 1 Status: In Progress Trigger Date: 27 May 2013 | Title: SC capability to send commands to the instruments Description: Having the capability of the SC computer to send a few commands to the instruments (less than a dozen commands needed) would mitigate the risk.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: More testing Description: All autonomy algorithms will need to be tested extensively.

## Slide 26: SPP PLANS: ISIS DDD EMI Requirement
Description ID: 11 | Given that the SPP Project is considering updating EMI requirements for Deep Dielectric Discharge, there is a chance that the Project will require all instrument box walls to be 54 mils thick;
Consequence | which would result in a significant mass increase to the ISIS instrument.
Overall Status: Accepted(Active) Consequence: 1 Likelihood: 5 | 
Status Message | Updated analysis demonstrates that mitigation is only required on external cables with restrictions on floating connectors in E-Box, per Rich Conde: "Deep dielectric discharges are possible on harnesses on the exterior of the spacecraft. Therefore any electrical interface to a harness that is fully or partially on the exterior of the spacecraft must satisfy the survival and operational requirements previously presented... Deep dielectric discharges in the external harness can be prevented with total shielding of 13 mils Al equivalent, which could be provided by an additional 3 wraps (with 50% overlap) of Neptape. There is an additional DDD-related requirement on the maximum allowable volume of floating dielectric or conductive material within a shielded enclosure such as a chassis." Information forthcoming
Mitigation Plan 1 Status: In Progress Trigger Date: 30 Jan 2013 | Title: Analyze and Quantify Impact Description: Work with the Project to fully analyze DDD environment and meter conservancy to reduce the requirement. ISIS team to quantify mass impact.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Implement Design Change Description: Increase wall thickness or spot shield to mitigate DDD dose.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2013 | Title: Discharge Protection Description: Add additional ground straps to mitigate surface charging and implement discharge protection methods.

## Slide 27: SPP PLANS: ISIS POL EMI Requirement
Description ID: 12 | Given that the SPP Project is considering updating EMI requirements to exclude switching circuits in power supplies, there is a chance that portions of the ISIS LVPS will have to be redesigned;
Consequence | which would result in a significant power increase due to loss of efficiency in non-switching supplies and a schedule delay in the delivery of the EM LVPS to EPI-Hi and EPI-Lo.
Overall Status: Accepted(Active) Consequence: 1 Likelihood: 1 | 
Status Message | The LVPS design does not use POL circuits
Mitigation Plan 1 Status: In Progress Trigger Date: 30 Jan 2013 | Title: Analyze and Quantify Impact Description: Work with the Project to fully analyze EMI environment and meter conservancy to reduce the requirement. ISIS team to quantify power/schedule impact.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Modify Design Description: Modify design to avoid use of POL converters.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Quantify Signature Description: Test and quantify ISIS frequency signature to correlate with FIELDS measurements on orbit.

## Slide 28: SPP PLANS: ISIS Worst Case Analysis Required for All Circuits
Description ID: 18 | Given that the project is requiring worst case circuit analysis to be performed on all circuits in the design, there is a chance that the ISIS team will be required to perform more analysis than was originally budgeted;
Consequence | which will result in increased cost and schedule delays.
Overall Status: Accepted(Active) Consequence: 1 Likelihood: 1 | 
Status Message | ISIS Worst Case Analysis reduced to only safety critical circuits.
Mitigation Plan 1 Status: Not Started Trigger Date: 27 May 2013 | Title: Negotiate a Reduced Set of Analyses Description: Perform analyses on mission and safety critical circuits in order to reduce the total cost of the analyses.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2013 | Title: Cost and Schedule Relief Description: Receive cost aid and schedule relief from project in order to implement worst case analysis on all circuits. This could result in engineers executing to a modified schedule and spend plan and/or the addition of new engineering resources.

## Slide 29: RISK: EPI-Hi Development of New PHASIC
Description ID: 2 | Given that design and fabrication of a new Rad-Hard PHASIC could prove prohibitively challenging; there is a risk that existing STEREO chips would need to be used,
Consequence | which will result in an increase in mass for spot shielding.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | Linearity of both low and high gain channels of prototyped PHASICs was verified to be "good" (max deviation from straight line fit is less than about 1 channel out of 2000, or 0.05% of full scale). Thermal noise appears to be somewhat lower than predictions, allowing low threshold goals to be met. This together with the good linearity in low gain means that the targeted improvement in dynamic range has been met. The remaining PHASIC mods that need to be checked are 1) that the matching of peak detector thresholds has been improved and 2) that the new preamp compensation scheme allows proper preamp gain/phase control and linearity for all detector configurations. Finally, we still need to check the performance over temperature.
Mitigation Plan 1 Status: In Progress Trigger Date: 01 May 2012 | Title: Radiation Hardened STEREO Design Description: Redesign STEREO PHASIC for new implementation with Aeroflex as a Rad-Hard ASIC. Assuming development progresses as expected, no severe delay in schedule is expected.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Oct 2014 | Title: Spot-Shield STEREO PHASIC Description: If problems arise with radiation-hardening the STEREO design, would use existing spare STEREO chips with spot shielding to reduce radiation dose to a tolerable level.

## Slide 30: RISK: EPI-Lo TOF ASIC Development
Description ID: 5 | Given that design and fabrication of an EPI-Lo TOF ASIC could prove prohibitively challenging; there is a risk that EPI-Lo will be required to use existing TOFAs,
Consequence | which will result in an increase in mass and power resources required and a decrease in performance.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | EPI-Lo has selected test house for final qualification and working with test house to develop tests and test procedures.
Mitigation Plan 1 Status: In Progress Trigger Date: 02 Apr 2012 | Title: Assist APL with Requirements Definition Description:
Backup Mitigation Plan Status: Not Started Trigger Date: 01 May 2014 | Title: Utilize Heritage Design Description: Ensure enough TOFAs are available for EPI-Lo. Potential mass/power increase and possible loss of performance.

## Slide 31: RISK: EPI-Lo Hot-Op Performance Impact
Description ID: 8 | Given that EPI-Lo has a max operating temperature of 30C and the Project expects EPI-Lo to operate at this temperature at Perihelion (prime science); there is a risk that operating at the max op temp will result in reduced resolution of the solid state detectors,
Consequence | which will result in a reduction in performance of the detector
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | EPI-Lo has received SSDs from Canberra and mounted them into Ultem carrier. Completed fabrication and assembly of energy board. Started testing SSD with energy board, but don't have test results yet.
Mitigation Plan 1 Status: Expired Trigger Date: 01 May 2012 | Title: Continued Analysis Description: Further analyze and quantify EPI-Lo’s performance at elevated temperatures to determine if expected temperatures pose a threat to instrument performance.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 May 2013 | Title: Add isolation to reduce temperature Description: Add thermal isolation between instrument electronics and instrument sensors to allow sensors to run at lower temperature. Could also operate instrument colder by using more heater power.

## Slide 32: RISK: EPI-Hi solar illumination
Description ID: 9 | Given that the spacecraft is planning to cant the spacecraft at 1AU in order to warm the radiators behind the heat shield; there is a chance that EPI-Hi windows will be facing the sun,
Consequence | which could result in thin windows covering LET telescopes to overheat and fail, possibly causing damage to the EPI-Hi detectors.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | Finished: Goddard solar simulator will work for EPI-Hi solar illumination test. In Process: Determine correct thermal coating for aluminized polyimide windows and run thermal analysis.
Mitigation Plan 1 Status: Implemented Trigger Date: 01 Aug 2012 | Title: Define Exposure Scenario Description: Obtain definition of planned illumination conditions (directions, durations) from project and work with project to determine if there is an approach that can be used to avoid excessive illumination of LET windows.
Mitigation Plan 2 Status: Expired Trigger Date: 01 Feb 2013 | Title: Thermal Analysis and Test Description: Do a thermal analysis of the window, once the window material and thickness are chosen. Do test of EM windows using a solar simulator at GSFC.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Oct 2013 | Title: Thicker Windows and Test Description: Make thicker windows that are in line with experience base of solar exposure at 1 AU. Do test of thicker EM windows using a solar simulator at GSFC.
Notes: SW: Says this should be a risk