## Slide 1: Instrument Development Status
Scott Weidner
Notes: introduction

## Slide 2: Outline
Key Dates
EPI-Hi EM Schedule
EPI-Lo EM Schedule
EPI-Hi FM Schedule
EPI-Lo EM Schedule
Critical Path, Reserves, and Slack
Schedule Threats and Mitigations
Summary

## Slide 3: ISIS Schedule Key Dates

## Slide 4: ISIS Schedule: EPI-Hi EM
<= Should Say EPI-Hi EM

## Slide 5: ISIS Schedule: EPI-Lo EM and Bracket

## Slide 6: ISIS Schedule: EPI-Hi FM
Insert FM Flow

## Slide 7: ISIS Schedule: EPI-Lo FM and Bracket
Insert FM Flow

## Slide 8: Critical Path, Reserves, and Slack
The ISIS Critical Path goes through [barry insert]
65 days of Reserves in-line with month/year reserves to delivery
Within the schedule, there is slack between tasks to keep schedule pushed to the left even beyond the Reserves
Earned Value already in use during Phase B to help keep a realistic picture of progress being made and provide early warning

## Slide 9: Schedule Threats and Mitigations
Schedule Threats
  TRL6 development and other Phase B work eliminated the most serious schedule threats
    New detectors, new ASIC designs
  Long-lead parts always need to be watched
    So far we’ve had excellent performance from Micron Semiconductor
  Interfaces between institutions require extra attention
    GSFC to Caltech with Mechanical and Detector Deliveries
    JHU/APL to Caltech with LVPS Deliveries
Mitigations
  Planner provides weekly Look-Ahead List to the ISIS team
  Weekly coordination meetings with all institutions
  EM testing used to mitigate FM schedule risks
  Earned Value Management provides early warning
  Planner provides detailed analysis and coordinates with SPP

## Slide 10: Summary
ISIS Team has performed well during Phase B
TRL 6 Achieved for all of the ISIS Technology Development
New design elements have been prototyped and tested
Requirements Defined
  Baseline of ICDs and Requirements Documents
Detailed Preliminary Design completed
  Schematics and mechanical designs Peer Reviewed
Early Analyses show good margins
Trade studies in Phase B have reduced risk
ISIS is on track to proceed into Phase C on schedule