## Slide 1: Risk Status
John Dickinson
ISIS SE (SwRI)
This document contains technical data that may be controlled by the International Traffic in Arms Regulations (22 CFR 120-130) and may not be provided, disclosed or transferred in any manner to any person, whether in the U.S. or abroad, who is not 1) a citizen of the United States, 2) a lawful permanent resident of the United States, or 3) a protected individual as defined by 8 USC 1324b(a)(3), without the written permission of the United States Department of State.

## Slide 2: Outline
Risk Mitigation Plan Overview
Team Member Roles
Risk Management Plan Flow
Risk Analysis Score Card
Risk Summary
Progress on Top Risks
Tracking the “life cycle” of one of the top risks
Summary

## Slide 3: Risk Mitigation Plan Overview
Team members constantly weigh potential risks
Team members can suggest a risk at any time
With team member input, SE enters risk into PIMS
Instrument leads generate risk mitigation plan including potential cost and schedule, technical, and safety impacts
SE assesses probability and consequences of risks
Once a mitigation strategy is selected by team and confirmed by SE/PM, it is executed
SE ensures risks are handled by assigning and tracking action items
Team members review risks in weekly meetings
PM and SE will continuously monitor and audit risk list
PM elevates risks that impact other instruments or ISIS resources to SPP Project in PIMS system (web-based tool, open to SPP)
PM and SE consensus is required for risk closure with SPP Project concurrence as needed

## Slide 4: Team Member Roles
Bottoms-up approach
All team members
  Assess threats to determine if any are risks
  Provide risk details to SE for entry into PIMS
  Analyze identified risks
Instrument Team Leads (Wiedenbeck/Cummings and McNutt/Seifert)
  Manage and report on instrument risks
  Determine mitigation strategies
  Determine how risks might affect the SPP mission
ISIS SE (Dickinson)
  Assist ISIS PM as needed, especially with technical input and analyses
  Review mitigation plans
  Address concerns from SPP Project Office
  Ensures risks are documented as appropriate
ISIS PM (Weidner)
  Oversee and manage risk list
  Work with SE and instrument teams to determine risk mitigation plans
  Report major risks to SPP Project in Monthly Risk Status Reports

## Slide 5: General RMP Flow

## Slide 6: Risk Analysis Score Card
Likelihood Bins | Safety (likelihood of safety event occurrences) | Technical (Estimated likelihood of not meeting mission technical performance requirements) | Cost/schedule (Estimated likelihood of not meeting allocated Cost/Schedule requirements or margin)
5 Very High | (Ps > 10-1) | (PT > 50%) | (PCS > 75%)
4 High | (10-2 < Ps ≤ 10-1) | (25% < PT ≤ 50%) | (50% < PCS ≤ 75%)
3 Moderate | (10-3 < Ps ≤ 10-2) | (15% < PT ≤ 25%) | (25% < PCS ≤ 50%)
2 Low | (10-6 < Ps ≤ 10-3) | (2% < PT ≤ 15%) | (10% < PCS ≤ 25%)
1 Very Low | (Ps ≤ 10-6) | (0.1% < PT ≤ 2%) | (PCS ≤ 10%)
LEVEL | Minimal (1) | Minor (2) | Medium (3) | Major (4) | Very High (5)
Safety | Negligible safety impact | Minor injury with no lost work time | Injury with lost work time | Severe injury | Death or permanent disabling injury
Technical | Negligible technical impact | Decrease in instrument capability/margin. But all instrument requirements met, or need for requirement definition or design/implementation workaround | Major loss of instrument capability | Loss of Instrument (EPI-Hi or EPI-Lo) | Loss of one or more Level-1 science requirements
Cost | ISIS Project cost overrun of less than 1% of allocated | ISIS Project cost overrun between 1% to 3% of allocated | ISIS Project cost overrun between 3% to 10% of allocated | ISIS Project cost overrun between 10% to 20% of allocated | ISIS Project cost overrun of greater than 20% of allocated
Schedule | Negligible schedule slip | Schedule slip not on critical path | Schedule slip affecting critical path but not launch or post-launch critical event | Schedule slip of 1 to 3 months | Schedule slip of greater than 3 months

## Slide 7
11 |  |  |  | 
13 17 |  |  |  | 
 | 7 14 | 6 19 |  | 
 | 1 2 3 5 8 9 | 4 15 16 |  | 
18 12 |  | 10 |  | 
Risk Summary
1 2 3 4 5 Consequence
Likelihood 1 2 3 4 5

## Slide 8
13 17 |  |  |  | 
 | 14 | 6 19 |  | 
 | 1 3 | 4 15 16 |  | 
Progress on Top Risks
1 2 3 4 5 Consequence
Likelihood 1 2 3 4 5
Rank | Trend | Risk ID | Approach | Risk Title
1 |  | 6 | R | ISIS Vibration Levels
2 |  | 19 | R | ISIS Increased Autonomy
3 |  | 14 | R | ISIS Shock Testing
4 |  | 4 | R | EPI-Lo Dust Impact Susceptibility
5 |  | 15 | R | ISIS Increased Ground Software Demands Due to Autonomy
6 |  | 16 | R | ISIS Increased Instrument FSW Demands Due to Autonomy
7 |  | 13 | R | ISIS Time Tagged Commands
8 |  | 17 | R | Configuring ISIS Based on Solar Distance
9 |  | 1 | R | EPI-Hi Thin Detector Availability
10 |  | 3 | R | EPI-Hi LET Thin Windows and Dust Impact Susceptibility
Med
High
Low
Criticality
L x C Trend
Decreasing (Improving)
Increasing (Worsening)
Unchanged
New Since Last Period
Approach
M - Mitigate
W - Watch
A - Accept
R - Research

## Slide 9: RISK: EPI-Hi LET Thin Windows and Dust Impact Susceptibility
Description ID: 3 | Given that thin windows are fragile and the mission dust environment could be harsher than initially expected; there is a risk that dust impacts could result in damage to the windows during flight,
Consequence | which will result in a compromise in the resolution of the EPI-Hi telescopes.
Overall Status: Accepted(Active) Consequence: 2 Likelihood: 2 | 
Status Message | EPI-Hi windows survived Heidelberg dust testing and showed stacked window configuration is effective at mitigating dust penetration to detectors. Even holes produced by penetrating particles result in very limited access of UV light to detectors.
Mitigation Plan 1 Status: Completed Trigger Date: 01 May 2013 | Title: Perform Dust Testing Description: The integrity of the windows in a stacked configuration will be tested in a dust environment to determine the efficacy of the windows in protecting the detectors from dust and maintaining structural integrity to block UV light.
Mitigation Plan 2 Status: Not Started Trigger Date: 01 Nov 2013 | Title: Baffling for Dust Protection Description: If risk of catastrophic damage due to dust impacts does not appear acceptably low, EPI-Hi could increase the baffle size to limit the affected angle of dust on the detectors. Trade: mass is used to buy down damage risk.
Backup Mitigation Plan Status: Not Started Trigger Date: 01 Nov 2014 | Title: Significant Thickness Increase Description: If risk of catastrophic damage due to dust impacts does not appear acceptably low, EPI-Hi could use significantly thicker window for LET2 (single ended) telescope. Trade: measurement quality is reduced to buy down catastrophic damage risk.

## Slide 10: Process: Initiation
Initial concerns about dust
  The SPP dust environment is not known
There are sensitive apertures on the ISIS instruments
  SSDs sensitive to UV light contamination (background noise)
The need for detector protection was known
  Windows were required to protect the detectors from UV light
  Various materials were allowable, so long as they were light-tight, had an outer surface with low α/ε
Realization that windows are sensitive
  While protective windows were expected in the design, it was not known what configuration would be required or adequate to mitigate the dust environment
A risk was written to capture the progress of this concern

## Slide 11: Process: Mitigation Approach
In order to mitigate the risk, more information was needed about the environment, the window configuration, and the response of the windows to dust impacts in the environment
ISIS worked with Doug Mehoke and the project to refine dust models
  ISIS actively participated in early discussions of the most appropriate dust model to apply to the mission
  Project ran simulations on the environment accounting for ISIS geometry to produce impact statistics
ISIS established a plan for testing of candidate windows at Heidelberg dust impact facility
  Few dust accelerator facilities in the world
  Dust impact plan was established
  Eric Christian travelled to Heidelberg with the samples to perform the test
ISIS used dust impact results to determine a viable window configuration

## Slide 12: Process: Mitigation - Dust Testing
Height image
3-D image
The diameter of the hole: ~2.1 µm
Foil #1, Hole A
Top Shown

## Slide 13: Process: Mitigation - Dust Testing
Note that there are some artifacts in all AFM images due to AFM tip shape and scanning speed
The height of the crater: ~0.9 µm
Height image
3-D image
Foil #1, Hole A Bottom Shown

## Slide 14: Process: Analysis and Results
Tests showed the Windows performed as we had hoped
Dust impacts did not propagate into large-scale tears
Affected regions remained on the order of the particle size
Triple stack of Windows effectively stopped lower energy particles (in some cases first two Windows were penetrated, but third was only dented)
Even when full penetration occurs, collimation provided by the stack of Windows limits UV background
Risk level was lowered through a combination of test and analysis

## Slide 15: Process: Road Map
8
Time
Likelihood + Consequence
7
6
5
4
3
2
1
Retired
3/5/12
Risk Initiation
L:2/C:4
Dust Testing
L:2/C:3
7/10/13
Analysis
L:2/C:2
9/30/13

## Slide 16: Summary
ISIS risk process is effective and active
Excellent coordination between SPP Project Team and ISIS in making analyses and running tests to reduce risk
ISIS has made good progress in driving down and mitigating early risks during Phase B
New risks will continue to be identified, and this process will be used to systematically work these risks down