## Slide 1: EPI-Hi Electronics
Branislav Kecman / Rick Cook
Notes: introduction

## Slide 2: EPI-Hi Electronics
Implementation and Status
Branislav Kecman
Cognizant Electrical Engineer

## Slide 3: Outline
Design/Assembly/Test Flow
Boards Status
  Layout Example
Parts Status
  Major Parts Used
  In-House Screening
Resources
  Power
  Mass
Harness Diagram
  Thermal Harness

## Slide 4: Design/Assembly/Test Flow
Preliminary design
and schematic
R. Cook
Detailed design
and schematic
J. Burnham
B. Kecman
Layout
J. Burnham
B. Kecman
Parts identification, EM and flight
B. Kecman
M. Windhausen (GSFC)
Parts stress
analysis
J. Burnham
EM assembly
J. Burnham
B. Kecman
Parts procurement, EM and flight
B. Kecman, M. Windhausen (GSFC)
Test/rework/test
R. Cook
B. Kecman
J. Burnham
Flight board
assembly & inspection
JPL
Layout review
C. Derksen
(JPL)
Flight board test
R. Cook
B. Kecman
J. Burnham
Staking,
conformal
coating
JPL

## Slide 5: Boards Status
Board | Sche-matics | Peer review | Layout | EM fab | EM parts procured | EM test schedule
Telescope (x 3) | 80% | √ | 10% | 0 | 60% | Feb ‘14
DPU | 100% | √ | ~100% | 0 | 90% | Dec ‘13
LVPS | 100% | √ | 100% | In process | 100% | Nov ‘13
Bias Supply | 100% | √ | 50% | 0 | 80% | Jan ‘14

## Slide 6: DPU Board Layout

## Slide 7: Parts Status
Parts list submitted to Parts Control Board for review
Will use spare flight parts from Caltech, GSFC, SwRI and JPL stock
Plan to test rad-hard PHASIC and HKchip die for TID and Latch-up at LBNL’s 88” Cyclotron
JPL will package PHASIC and HKchip
Screening specs for PHASIC and HKchip submitted to PCB for review

## Slide 8: Major Parts Used
Microsemi/Actel FPGA, RTAX250SL-CQ208B, heritage NuSTAR
Aeroflex SRAM 16Mb (512k x 32), UT8CR512K32
Aeroflex SRAM 4Mb (128k x 32), UT8R128K32, heritage NuSTAR
Aeroflex MRAM 16Mb (2M x 8), UT8MR2M8
PHASIC hybrid, heritage STEREO
HKchip

## Slide 9: In-House Screening

## Slide 10: Resources - Power
End Of Life | 
Bias Supply @ End Of Life | 0.68
LVPS @ EOL (70% efficiency) | 1.74
Total @ EOL | 5.8
Subsystem | Power [ W ]
LET1 board | 1.06
LET2 board | 0.76
HET board | 0.95
DPU board | 0.62
Bias Supply @ Beginning Of Life | 0.12
LVPS @ BOL (70% efficiency) | 1.50
Total @ BOL | 5.0

## Slide 11: Resources - Mass
Subsystem | Mass [ g ]
LET1 telescope LET1 board | 225 258
LET2 telescope LET2 board | 145 233
HET telescope HET board | 120 250
DPU board Bias Supply & RF shields LVPS & RF shields | 197 225 + 130 160 + 100
Elec. box, hardware & shielding Telescope brackets Thermal hardware MLI blankets | 925 + 250 +100 160 50 100
Total | 3,628

## Slide 12: Harness Diagram

## Slide 13: Thermal Harness Diagram