## Sensor Actions
EPI-Lo Sensor Review - May 22, 2013
Identification Number | Reviewer | Actionee | Area of Concern | Concern | Recommended Action | Date Opened | Due Date | Action Response
1 | Scott Weidner | Ken Nelson | Anode board | HV Guarding | Make ground "targets" surrounding HV on a LV side of the PWB to protect LV circuitry from discharges | 2013-05-22 | 2013-07-04 | Completed.
2 | Susan Pope | Steve Layman | 3Kv Lug Connection | Extra parts covering this lug connection provides extra surface | Remove Ultem cover and associated spring washer (slide 11) on 3Kv lug connection | 2013-05-22 | 2013-07-04 | Parts have been deleted.
3 | Susan Pope | Steve Layman | MCP holder 900V connection | Increased spacing from 1000V to 900V at connection point | Make 900V guard washer out of plastic and eliminate Kapton spacer | 2013-05-22 | 2013-07-04 | Guard washer removed. Lug redesigned.
4 | Susan Pope | Steve Layman | Venting | Unvented volumes are virtual leak. The local increase in pressure can lead to HV breakdown. | Vent all fasteners. (1) Vented Screws (2) Vent trapped volume sideways by drilling in below threads | 2013-05-22 | 2013-07-04 | Will incorporate into the design.
5 | Steve Jaskulek | Steve Layman | Wedges | UV | Use aluminum tape to close the gaps between the wedges for UV purposes | 2013-05-22 | 2013-07-04 | Will know more when we assemble. Will use it if needed.
6 | Steve Jaskulek | Steve Layman | Wedges |  | Consider using bevel washer on screw for the 1000 volt to the side wall to avoid loss of contact due to material creep | 2013-05-22 | 2013-07-04 | Will use bevel washers.
7 | Steve Jaskulek | Ken Nelson | Anode board |  | The separation distance around the 3000V components on the anode board component side have only 1000/mm spacing along the board surface. This needs to be increased. Is the decoupling 3000V cap even needed? | 2013-05-22 | 2013-07-04 | Increased as much as possible.
8 | Steve Jaskulek | Ken Nelson | HV testing |  | If HV standoff is run at room temperature rather than our expected max temp in test/qual, we may need to increase the HV (e.g. 3600 --> 4000) to compensate. | 2013-05-22 | 2013-07-04 | Run HV stand off test with heaters
9 | Steve Jaskulek | Steve Layman | Wedges |  | Reshape the 1Kv lug to provide more separation from the side wall, and open hole. The 2-9 Kv lug is even worse. | 2013-05-22 | 2013-07-04 | Redesigned to a "dog leg."
10 | Steve Jaskulek | Ken Nelson | HV testing | Discharge monitoring must use partial discharge circuits, not just use the HV supply trip. | Use blocking cap and CSA to look for discharges. | 2013-05-22 | 2013-07-04 | Will employ CSA in future testing.
11 | Ken Nelson | Scott Weidner | Anode board |  | Give identifier of Kapton sheet used in PWB stackup for IES | 2013-05-22 | 2013-07-04 | Information sent to APL.
12 | Don Mitchell | Steve Layman |  | The insulator between the cover and the 1 kV volume spans a gap of 2mm. | It should be shaped so that the surface path along the insulator surface is at least 3mm. For example, "T" shaped or "U" shaped. | 2013-05-22 | 2013-07-04 | We will modify to accommodate request.
Updated 7-9-2013